## Slide 1: SuperBigBite DAQ update
Bryan Moffit
Jefferson Lab
SBS DOE Review – November 2015

## Slide 2: Outline
SBS requirements
  Data Event Flow
Fastbus Readout
  Event Switching
FADC HCAL readout
GEM readout
Timeline
Manpower

## Slide 3: DAQ requirements
Focal Plane Polarimeter
  Front tracker
  Back tracker GEM 128 K channels
  288 channels HCAL on FADC ( 10 samples )
Electron detector
  1800 channels ECAL
  CDet 2152 Channels ( TDC )

## Slide 4: event size (after deconvolution)
Detector | Channels | Single rate Hz | Occupancy 75 ns in % | Channels firing | Event size (bytes) | Data rate 5 KHz MB/s
Front tracker | 41,000 | 3.3e9 | 18.1 | 7430 | 136,000 | 90
Back tracker | 112,640 | 3.36e9 | 22.4 | 12600 | 230,000 | 150
HCal | 288 | _ | 100 | 288 | 7,200 | 36
ECAL | 1800 + 225 | _ | 100 | 2025 | 8,100 | 45
CDET | 2152 | _ | 10 | 216 | 864 | 4.3
Total |  |  |  |  |  | 325.3 MB/s
HCAL and ECAL occupancies need to be evaluated : using 100 % for now
Includes geometrical matching

## Slide 5: DAQ requirements
Bigbite
  GEM 128 K channels
  Shower 189 blocks (ADC)
  Preshower 54 blocks (ADC)
  Scintillator 180 bars 360 PMTs ( ADC/TDC)
  Cerenkov 550 PMTs (TDC)
Neutron detector
  288 channels HCAL ( FADC + high res TDC )
  CDet 2152 Channels ( TDC )

## Slide 6: event size (after deconvolution)
Arm | Detector | Channels | Single rate Hz | Occupancy 75 ns in % | Channels firing | Event size (bytes) | Data rate 5 KHz MB/s
BigBite | GEM | 112,640 | 2.6e9 | 8.7 | 5248 | 62,976 | 300
 | Lead glass | 243 | _ | 100 | 243 | 1003 | 5
 | Scintillators | 360 | _ | 100 | 360 | 1485 | 7.4
 | Cerenkov | 550 | _ | 100 | 550 | 2269 | 11.34
Neutron | HCal | 288 | _ | 100 | 288 | 7,200 | 36
 | HCAL time | 288 | _ | 100 | 288 | 1170 | 5.85
 | CDET | 2152 | _ | 10 | 216 | 864 | 4.3
Total at 5 KHz 370 MB/s Max

## Slide 7: Fastbus update
Use new CODA 3.0 TI and TS
  More flexibility in programming
  Event blocking
  Absolute timestamp for synchronization check
  Trigger partitioning capability only use a subset of modules
Asked for modified firmware to DAQ group in May 2015 ( William Gu and Bryan Moffit )
Firmware being developed and tested

## Slide 8: Fastbus update
Have sufficient TDCs, ADCs, crates, SFI, aux. cards
Making FB faster
  sparsification – works
  event blocking – works
  event switching – being tested
  merging with pipelining VME – to be tried
Three large Fastbus systems assembled in the test lab.
have 113
need 94
have 236
need 124
have 30
need 21
have 15 (20 being made)
need 30
have 21
need 21

## Slide 9: DAQ Configuration / both arms
T2 distributed to Hadron and Electron Arms
L2
Fastbus
TI provides timestamp for every event
If no L2A, Fast Clear to Fastbus
ECAL
ECAL trigger
ECAL
Sums
Trigger
SSP x 3

## Slide 10
HallA SBS Trigger block diagram
Lookup table
32x1
Trigger Rule
Local Trigger
distribution
Delay
Delay
Delay
Delay
Width
Width
Width
Width
Width Ext
Match
Match
Match
Match
Width
Width
Width
Width
Trigger
word
Serializer
Serializer/Fiber
Serializer/Fiber
Delay, Prescale,
Lookup table,
Trigger Rule
Delay/Width
second
word
Local Trigger
ReadOut Trigger
Gate / Common Stop
Fast
Clear
BUSY
Readout Module Data

## Slide 11: Single Crate vs. Trigger Switching
Readout trigger rate ~ 5 kHz
Buffer Level = 4
8ADC - (reading pedestals on 6 channels in each ADC)

## Slide 12: HCAL
All FADC 16 delivered
2 VXS crates delivered
2 Intel Concurrent CPU delivered
Readout tested
Development of trigger using HPS firmware and Global Trigger Processor (GTP)
New VTP ordered

## Slide 13: HCAL FADC electronics
Cosmics from calorimeter block
Will test later with HCAL module

## Slide 14: Hadron Arm - HCAL DAQ: proton trigger
2 VME switched Serial (VXS) Crates
JLAB FADC250, a 16-channel 12-bit FADC sampling at 250 MHz
  16 FADC in VXS Crate 1
  2 FADC in VXS Crate 2
  If signal pass threshold
    Integrates signal and subtracts pedestal
    Sends time frame info
HCal Signals to FADC inputs
VTP (Crate Trigger Processor)
  Located in VXS crates
  Collects integrated signal and timing from FADC channels
  Sends data to the second VTP for clustering

## Slide 15: HCAL trigger development
HPS firmware installed on FADC and GTP
FADC readout tested with cosmics
Testing triggering capability
Need
  implement decoder for analysis
  Test using 2 crates and new VTP

## Slide 16: GEM MPD readout
INFN MPD used for several years using custom C++ package
Package ported to intel CPU
New C library written for easy integration into CODA
( Bryan Moffit, Evaristo Cisbani, Danning Di )
CODA configuration running
Debugging module initialization

## Slide 17: GEM optical link readout
Aurora protocol based
  Implemented by Paolo Musico. To be tested.
2 Gbit optical link to SubSystem Processor (SSP) module
  250 MB/s per link
Readout up to 32 MPD in parallel
  8 GB/s bandwidth compared to ~100 MB/s using VME
SSP library
  Readout routines – Completed.
  MPD configuration routines – In progress
Link from MPD to SSP module
  Implemented by Ben Raydo. Works.

## Slide 18: Timeline
4th quarter 2015 | 1st quarter 2016 | 2st quarter 2016 | Future
Finish MPD CODA readout – debug Finish Fastbus Readout – debug Small scale setup 200 KHz L1 5 kHz coinc Fastbus, MPD, and HCAL FADC Cdet Fastbus Analysis software : check synchronization Test MPD optical readout (SSP) HCAL trigger ordered | Implement new HCAL Trigger module HCAL cosmics GEM cosmics with MPD Test GEM readout with optical link in high background at UVA Develop GEM analysis software | GEM installed on BigBite for tritium experiment ECal cosmics DVCS experiment Parasitic test: Fastbus and FADC setup | Tritium experiment Parasitic test: Fastbus and FADC setup

## Slide 19: Manpower
Fastbus
  JLAB : Dasuni Adikaram, Mark Jones, Robert Michaels, Bryan Moffit, William Gu
MPD
  INFN : Evaristo Cisbani, Paolo Musico
  UVA : Danning Di, Kondo Gnanvo, Nilanga Liyanage
  JLAB : Ben Raydo, Bryan Moffit
  Stony Brook : Seamus Riordan
HCAL
  JLAB : Alexandre Camsonne, Ben Raydo, Bryan Moffit

## Slide 20: Conclusion
Fastbus event switching works well
  Preliminary results show acceptable dead time in experiment conditions
  Need to develop software and check synchronization
HCAL:
  FADC ready
  trigger implemented and being tested
MPD:
  CODA readout implemented
  Debugging of the software driver
  Optical readout in progress
Small scale test setup in a few weeks

## Slide 21: Backup Slides

## Slide 22: GEp5
Focal Plane Polarimeter
  Front tracker
  Back tracker GEM 128 K channels
  288 channels HCAL on FADC ( 10 samples )
Electron detector
  1800 channels ECAL
  CDet 2152 Channels ( TDC )

## Slide 23: GEM data flow GEp
GEM
153 640
strips
MPD
153 640
X 6 samples x 3 bytes
FT=5.99 GB/s
BT=10.2 GB/s
Total= 16.2 GB/s
5 KHz trigger rate
MPD
Zero suppress
FT=1.63GB/s
BT=2.76 GB/s
Geometrical cut (factor 3)
FT=0.53 GB/s
BT=0.9 GB/s
Analog
SSP
Deconvolution
( factor 2)
FT=0.26 GB/s
BT=0.45GB/s
Keep Amplitude and time (3)
FT=0.09 GB/s
BT=0.15 GB/s
Total
240 MB/s
Time window | 6x25 ns | 3x25 ns
Occupancy forward tracker in % | 36.2 | 18.1
Occupancy back tracker In % | 22.4 | 11.2
Need to test clustering and correlations betweens planes for further reduction
Assume 2.5 strips cluster size

## Slide 24: GEp5 event size ( after deconvolution and geomtrical matching)
Detector | Channels | Single rate Hz | Occupancy 75 ns in % | Channels firing | Event size (bytes) | Data rate 5 KHz MB/s
Front tracker | 41,000 | 3.3e9 | 18.1 | 7430 | 136,000 | 90
Back tracker | 128,000 | 3.36e9 | 22.4 | 12600 | 230,000 | 150
HCal | 288 | _ | 100 | 288 | 7,200 | 36
ECAL | 1800 + 225 | _ | 100 | 2025 | 8,100 | 45
CDET | 2152 | _ | 10 | 216 | 864 | 4.3
Total |  |  |  |  |  | 325.3 MB/s
HCAL and ECAL occupancies need to be evaluated : using 100 % for now

## Slide 25
ECAL
1800
Channels
225 sums
HCAL
288
Channels
Optical 83x100 Mbit=10 GB/s
GEM
153,640
Channels
Analog
MPD
83 Boards
16.2 GB/s in
1430 MB/s out
(zero suppress, matching)
SSP
3 Boards
1430 MB/s in
Deconvolution
715 MB/s
Keep A and T
240 MB/s
VME
CPU
VME bus 3x100 MB/s
DAQ
Computer
325.3 MB/s
CDet
1176x2=
2352
Channels
FADC
18
Boards
36 MB/s
VME
CPU
VME bus 2x100 MB\s
1 Gbit
Ethernet x3
= 375 MB/s max
1 Gbit Ethernet x2
= 250 MB/s max
Fastbus
96 Boards in 12 crates
45 MB/s = 3.5 MB/s per crate
Fastbus
87 boards in 9 crates
Boards
4.3 MB/s = 1.1 MB/s crate
Swi
tch
1 Gbit Ethernet
x12
100 Mbit Ethernet
x9
1 Gbit Ethernet x2
250 MB/s max
VME
CPU
VME bus 12x20 MB\s
VME
CPU
VME bus 9x20 MB\s
Typical SSD
has
500 MB/s rate

## Slide 26: GEn and GMn
Bigbite
  GEM 128 K channels
  Shower 189 blocks (ADC)
  Preshower 54 blocks (ADC)
  Scintillator 180 bars 360 PMTs ( ADC/TDC)
  Cerenkov 550 PMTs (TDC)
Neutron detector
  288 channels HCAL ( FADC + high res TDC )
  CDet 2152 Channels ( TDC )

## Slide 27: Gen trigger rates ( 95 % QE peak )
Q^2 | Rate [kHz]
1.5 | 3
4 | 0.4
7 | 0.09
10 | 0.06

## Slide 28: GEM data flow GEp
GEM
112 640
strips
55 MPDs
112 640
X 6 samples x 3 bytes
= 10.3 GB/s
5 KHz trigger rate
MPD
Zero suppress
= 1.8 GB/s
Analog
SSP
Deconvolution
( factor 2)
= 0.9 GB/s
Keep A & T
(factor 3)
=0.3 GB/s
Time window | 6x25 ns | 3x25 ns
Occupancy back tracker In % | 17.4 | 8.7
Assume each MPD word packed on 24 bits = 3 bytes

## Slide 29: Gen and GMn event size
Arm | Detector | Channels | Single rate Hz | Occupancy 150 ns in % | Channels firing | Event size (bytes) | Data rate 5 KHz MB/s
BigBite | GEM | 112,640 | 2.6e9 | 17.4 | 19680 | 359,775 | 1798
 | Lead glass | 243 | _ | 100 | 243 | 1003 | 5
 | Scintillators | 360 | _ | 100 | 360 | 1485 | 7.4
 | Cerenkov | 550 | _ | 100 | 550 | 2269 | 11.34
Neutron | HCal | 288 | _ | 100 | 288 | 7,200 | 36
 | HCAL time | 288 | _ | 100 | 288 | 1170 | 5.85
 | CDET | 2152 | _ | 10 | 216 | 864 | 4.3

## Slide 30: Gen and GMn event size deconvoluted
Arm | Detector | Channels | Single rate Hz | Occupancy 100 ns in % | Channels firing | Event size (bytes) | Data rate 5 KHz MB/s
BigBite | GEM | 112,640 | 2.6e9 | 8.7 | 5248 | 62,976 | 300
 | Lead glass | 243 | _ | 100 | 243 | 1003 | 5
 | Scintillators | 360 | _ | 100 | 360 | 1485 | 7.4
 | Cerenkov | 550 | _ | 100 | 550 | 2269 | 11.34
Neutron | HCal | 288 | _ | 100 | 288 | 7,200 | 36
 | HCAL time | 288 | _ | 100 | 288 | 1170 | 5.85
 | CDET | 2152 | _ | 10 | 216 | 864 | 4.3
Total at 5 KHz 369.89 MB/s Max

## Slide 31
Bigbite
ADC
1153 channels
HCAL
288
Channels
Optical 83x100 Mbit=10 GB/s
GEM
112,640
Channels
Analog
MPD
55 Boards
1,030 MB/s in
1,800 MB/s out
(zero suppress)
SSP
3 Boards
1800 MB/s in
Deconvolution
300 MB/s out
VME
CPU
VME bus 2x100 MB/s
DAQ
Computer
369.9 MB/s
CDet
1176x2=
2352
Channels
FADC + TDC
18
Boards
42 MB/s
VME
CPU
VME bus 2x100 MB\s
1 Gbit
Ethernet x2
= 250 MB/s max
1 Gbit Ethernet x2
= 250 MB/s max
Fastbus
56 Boards in 12 crates
23.8 MB/s = 1.9 MB/s per crate
Fastbus
87 boards in 9 crates
Boards
4.3 MB/s = 1.1 MB/s crate
Swi
tch
1 Gbit Ethernet
x12
100 Mbit Ethernet
x9
1 Gbit Ethernet x2
250 MB/s max
VME
CPU
VME bus 12x20 MB\s
VME
CPU
VME bus 9x20 MB\s

## Slide 32: SILO
DAQ computer
10 GigE
IBM TS3500 9 frames ( up to 15 )
( up to 12 drives per frame)
10 LTO 5 1.5 TB 140 MB/s
6 LTO 6 2.5 TB 160 MB/s
(LTO7 6 TB 300 MB/s)
1.25 GB/s
Disk array
SSD or RAID
TS3500 frame 1000 slots : 25 K$
Data mover 10 K$ each 160 MB/s

## Slide 33: Tape cost 250 MB/s
 |  | Days | Data rate | Seconds | Total data TB | Double | DLO5 in $ | DLO6 in $ | Tape DLO6
E12-12-09-019 | GMN | 25 | 250 | 2160000 | 540 | 1080 | 54000 | 32400 | 216
E12-09-016 | GEN | 50 | 250 | 4320000 | 1080 | 2160 | 108000 | 64800 | 432
E12-07-109 | GEP/GMP | 45 | 250 | 3888000 | 972 | 1944 | 97200 | 58320 | 388.8
E12-09-018 | SIDIS | 64 | 250 | 5529600 | 1382.4 | 2764.8 | 138240 | 82944 | 552.96
 | Total | 184 |  | 15897600 | 3974.4 | 7948.8 | 397440 | 238464 | 1589.76
Actual days | Actual years |  | Time in s |  |  | Per year | 394200 | 236520 | 
368 | 1.01 | 184 | 15897600 |  |  |  |  |  | 
1 600 LTO6 tapes for 240 K$, if go to 500 MB/s 480 K$
2 frames with 8 data movers 130 K$

## Slide 34: Conclusion
Estimated rate for max 5 KHz ( expect to run at 2 to 3 KHz )
325.3 MB/s for GEp5
370 MB/s for GEn ( no geometrical correlation)
Will work on clustering and plane coincidence in SSP, reduction factor to be determined using simulation
Need implement hardware and test