## Slide 1: SuperBigBite DAQ update
Bryan Moffit
Jefferson Lab
SBS DOE Review – November 2015

## Slide 2: Outline
SBS requirements
Fastbus Readout
FADC HCAL readout
GEM readout
Timeline
Manpower

## Slide 3: SBS DAQ requirements
  200 kHz L1, 3 kHz of L2 Electromagnetic Calorimeter Fastbus
  Coordinate detector Fastbus readout 1877S
  GEM readout VME
  HCAL trigger pipeline FADC and L2 trigger
/
  Bigbite readout Fastbus
  HCAL as neutron detector using FADC and high resolution TDC

## Slide 4: Fastbus update
Use new CODA 3.0 TI and TS
  More flexibility in programming
  Event blocking
  Absolute timestamp for synchronization check
  Trigger partitioning capability only use a subset of modules
Asked for modified firmware to DAQ group in May 2015 ( William Gu and Bryan Moffit )
Firmware being developed and tested

## Slide 5: Fastbus update
Have sufficient TDCs, ADCs, crates, SFI, aux. cards
Making FB faster
  sparsification – works
  event blocking – works
  event switching – being tested
  merging with pipelining VME – to be tried
Three large Fastbus systems assembled in the test lab.
have 113
need 94
have 236
need 124
have 30
need 21
have 15 (20 being made)
need 30
have 21
need 21

## Slide 6: DAQ Configuration / both arms
T2 distributed to Hadron and Electron Arms;
if no L2A, Fast Clear to Fastbus
L2
L2
L2
Fastbus

## Slide 7
HallA SBS Trigger block diagram
Lookup table
32x1
Trigger Rule
Local Trigger
distribution
Delay
Delay
Delay
Delay
Width
Width
Width
Width
Width Ext
Match
Match
Match
Match
Width
Width
Width
Width
Trigger
word
Serializer
Serializer/Fiber
Serializer/Fiber
Delay, Prescale,
Lookup table,
Trigger Rule
Delay/Width
second
word
Local Trigger
ReadOut Trigger
Gate / Common Stop
Fast
Clear
BUSY
Readout Module Data

## Slide 8: Pedestal Suppression
Chart: Readout trigger rate (Hz)
| 1145.4000000000001 | 8119.1 | 10814.7 | 4913.8999999999996 | 13093.1 | 16890 | 22452.5
Local_50kHz_pedeSup | 10.11 | 14.5977 | 15.7434 | 12.9205 | 17.3198 | 23.0432 | 34.8999
Local_100kHz_pedeSup | 18.5354 | 18.9397 | 20.5634 | 21.208 | 23.132 | 28.9388 | 37.0528
Local_50kHz_pedeSup | 25.6377 | 26.7435 | 27.9307 | 28.9473 | 30.2244 | 35.8366 | 40.8775
Local_50kHz_NopedSup | 24.8035 | 42.9484 | 12.4653 | 10.0686 | 57.4176 | 72.4219 | 81.83 | 85.1154 | 13.2788 | 12.0928
Local_100kHz_NopedSup | 19.7471 | 20.6118 | 22.0903 | 37.7701 | 53.8329 | 67.5743 | 78.1296 | 84.5678
Local_200kHz_NopedSup | 25.1119 | 26.1958 | 38.9807 | 52.4029 | 34.3715 | 69.9737 | 79.109 | 28.0518
No Pedestal
Suppression (8ADCs)
Pedestal
Suppressed
Single Crate
8 ADCs
Buffer level = 4
Local trigger ~ 50 kHz
Local trigger ~ 100 kHz
Local trigger ~ 200 kHz
Expected ~ 5000 Hz
Dead time at
Local ~ 200 kHz and Readout ~5kHz
D1 ~40%

## Slide 9: Trigger Switching
Expected ~ 5000 Hz
Chart: Readout trigger rate (Hz)
| 1320.7 | 2386.5 | 4041.6 | 5123.1000000000004 | 7289.6 | 10800.7 | 16088.4 | 22848.400000000001
Single | 19.7471 | 20.6118 | 22.0903 | 37.7701 | 53.8329 | 67.5743 | 78.1296 | 84.5678
3Crates | 2.338 | 2.2167 | 23.8158 | 9.2238 | 37.8864 | 44.0168 | 34.4805 | 31.8351 | 8.8881 | 6.7969 | 4.1572 | 2.8746 | 1.4263
Dead time at
Readout ~5kHz
D3 ~6%
D3 ~ (D1)3
No pedestal suppression (8ADC)
Local trigger rate ~ 100kHz

## Slide 10: HCAL
All FADC 16 delivered
2 VXS crates delivered
2 Intel Concurrent CPU delivered
Readout tested
Development of trigger using HPS firmware and GTP
New VTP ordered

## Slide 11: HCAL FADC electronics
Cosmics from calorimeter block
Will test later with HCAL module

## Slide 12: Hadron Arm - HCAL DAQ: proton trigger
2 VME switched Serial (VXS) Crates
JLAB FADC250, a 16-channel 12-bit FADC sampling at 250 MHz
  16 FADC in VXS Crate 1
  2 FADC in VXS Crate 2
  If signal pass threshold
    Integrates signal and subtracts pedestal
    Sends time frame info
HCal Signals to FADC inputs
VTP (Crate Trigger Processor)
  Located in VXS crates
  Collects integrated signal and timing from FADC channels
  Sends data to the second VTP for clustering

## Slide 13: HCAL trigger development
HPS firmware installed on FADC and GTP
FADC readout tested with cosmics
Testing triggering capability
Need
  implement decoder for analysis
  Test using 2 crates and new VTP

## Slide 14: GEM MPD readout
INFN MPD used for several years using custom C++ package
Package ported to intel CPU
New C library written for easy integration into CODA
( Bryan Moffit, Evaristo Cisbani, Danning Di )
CODA configuration running
Debugging module initialization

## Slide 15: Status MPD
VME part works
Data structure looks fine but data from APV has unexpected small dispersion
Maybe issue with APV configuration (I2C timing)
  being investigated

## Slide 16: GEM optical link readout
Aurora protocol based
  Implemented by Paolo Musico. To be tested.
2 Gbit optical link
  250 MB/s per link
Readout up to 32 MPD in parallel
  8 GB/s bandwidth compared to ~100 MB/s using VME
SSP library
  Readout routines – Completed.
  MPD configuration routines – In progress
Link from MPD to SSP module
  Implemented by Ben Raydo. Works.

## Slide 17: Timeline
4th quarter 2015 | 1st quarter 2016 | 2st quarter 2016 | Future
Finish MPD CODA readout – debug Finish Fastbus Readout – debug Small scale setup 200 KHz L1 5 kHz coinc Fastbus, MPD, and HCAL FADC Cdet Fastbus Analysis software : check synchronization Test MPD optical readout HCAL trigger ordered | Implement new HCAL Trigger module HCAL cosmics GEM cosmics with MPD Test GEM readout with optical link in high background at UVA Develop GEM analysis software | GEM installed on BigBite for tritium experiment ECal cosmics Parasitic test during DVCS : Fastbus and FADC setup | Tritium experiment Parasitic test during Tritium : Fastbus and FADC setup

## Slide 18: Manpower
Fastbus
  JLAB : Dasuni Adikaram, Mark Jones, Robert Michaels, Bryan Moffit, William Gu
MPD
  INFN : Evaristo Cisbani, Paolo Musico
  UVA : Danning Di, Kondo Gnanvo, Nilanga Liyanage
  JLAB : Ben Raydo, Bryan Moffit
  Stony Brook : Seamus Riordan
HCAL
  JLAB : Alexandre Camsonne, Ben Raydo, Bryan Moffit

## Slide 19: Conclusion
Fastbus flipping module close to be complete
  Preliminary results show acceptable dead time in experiment conditions
  Need to develop software and check synchronization
HCAL:
  FADC ready
  trigger implemented and being tested
MPD:
  CODA readout implemented
  Debugging of the software driver
  Optical readout in progress
Small scale test setup in a few weeks

## Slide 20: Trigger Switching – near 5 kHz
Chart: Local trigger rate (Hz)
| 44669.2 | 104913.7 | 150700.4 | 194717.3 | 27297.9 | 11369.4 | 199979.1 | 170920.4 | 65165.5 | 83922.7 | 8182.8
buffer4_3daq_nopedsup | 2.5099 | 3.7419 | 4.1961 | 6.5882 | 2.0287 | 1.3511 | 6.8404 | 5.2867 | 3.0341 | 3.6757 | 1.1329
 | 1.7391 | 2.3606 | 2.6502 | 4.4902 | 6.5756 | 9.4732 | 11.1386 | 17.5771
 | 26.3999 | 26.1214 | 27.5933 | 28.7049 | 28.0324 | 28.1751
3 crates
2 crates
1 crates
No pedestal suppression (8ADC)
Readout trigger rate ~ 5kHz